## project
Project Planner
[6 empty] | Period Highlight: |  |  |  |  | 1 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Entire project and PDF | 1 | 37 | 1 | 0 | 20%
Make Gantt chart | 1 | 2 | 1 | 2 | 100%
Concept generation | 1 | 5 | 1 | 0 | 60%
Make list of tasks required by robot | 1 | 2 | 2 | 1 | 100%
Establish relevant design specifications | 1 | 2 | 1 | 2 | 100%
Develop project plan | 1 | 3 | 1 | 0 | 85%
Generate and evaluate several design concepts | 1 | 5 | 1 | 0 | 40%
Establish customer needs | 2 | 4 | 2 | 0 | 60%
Summary report I | 2 | 1 | 2 | 1 | 100%
Prep for design review I | 2 | 1 | 2 | 0 | 95%
Concept Selection | 2 | 6 | 0 | 0 | 0%
Create concept specific specs | 3 | 7 | 0 | 0 | 0%
Functional idea codes for concepts | 4 | 6 | 0 | 0 | 10%
Prep concepts for CAD | 6 | 2 | 0 | 0 | 15%
Develop detailed design with CAD | 6 | 5 | 0 | 0 | 5%
Create solid works model | 6 | 5 | 0 | 0 | 5%
Develop manufacturing-ready design documentation | 9 | 7 | 0 | 0 | 0%
Use design simulation to analyze product performance | 9 | 4 | 0 | 0 | 0%
Develop prototype of design | 10 | 3 | 0 | 0 | 0%
Build robot | 12 | 6 | 0 | 0 | 0%
Final programming of robot | 16 | 8 | 0 | 0 | 0%
Summary report II | 20 | 4 | 0 | 0 | 0%
Prep for design review II | 22 | 2 | 0 | 0 | 0%
Evaluate prototype performance | 23 | 11 | 0 | 0 | 0%
Iterate on design | 24 | 10 | 0 | 0 | 0%
Debug the programs | 26 | 8 | 0 | 0 | 0%